## Vplan
Total Items | 39
Pass Items | 38
Fail Items | 1
NY Items
Section | Main Title | Description | Testname | Priority | Method | Owner | Status | Milestone | Remark
1 | Register test |  |  |  |  | Nguyễn Vy
1.1 | Read default value | 1. Wait for reset and clock stable 2. Read value of 4 register Pass condition: Check value matching with default value mention in RTL spec | reg_def_test | High | Directed |  | PASSED | 18/9
1.2 | Read and Write value check | 1. Wait for reset and clock stable 2. Write random value of 4 register 3. Read value of 4 register Pass condition: Check value matching | reg_rw_test |  | Directed |  | PASSED | 18/9
1.3 | Reset on the fly check | 1. Wait for reset and clock stable 2. Write random value of 4 register 3. Reset system 4. Read value of 4 register Pass condition: Check value matching with default value mention in RTL spec | reg_rs_test |  | Directed |  | PASSED | 18/9
1.4 | Check reserved register | 1. Wait for reset and clock stable 2. Write random value of reserved register 3. Read value of reserved register Pass condition: Check value equal is 0 | reg_reserved_test |  | Directed |  | PASSED | 18/9
1.5 | Check interrupt in TSR register | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h01 to TCR register 4. Wait interrupt is asserted 5. Write data 8'h00 to TSR register 6. Read value of TSR register 7. Write data 8'b01 to TSR register 8. Read value of TSR register 9. Write data 8'b11 to TCR register 10. Wait interrupt is asserted 11. Write data 8'b00 to TSR register 12. Read value of TSR register 13. Write data 8'b10 to TSR register 14. Read value of TSR register Pass condition: Check underflow bit and overflow bit is matching | reg_tsr_test |  | Directed |  | PASSED | 18/9
2 | Clock divsor test | [5 empty] | NYST
2.1 | No divide | [5 empty] | NY
2.2 | Divide by 2
2.3 | Divide by 4
2.4 | Divide by 8
2.5 | Divisor with Load
2 | Counter combine with divisor test
2.1 | Count up
2.1.1 | Count from 0, no divide | 1. Wait for reset and clock stable 2. Write data 8'b01 to TIE register 3. Write data 8'b01 to TCR register 4. Wait 300 posedege ker_clk 5. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_div1_test | High | Directed |  | PASSED | 20/9
2.1.2 | Count from 0, divide by 2 | 1. Wait for reset and clock stable 2. Write data 8'b01 to TIE register 3. Write data 8'b1001 to TCR register 4. Wait 600 posedege ker_clk 5. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_div2_test | Medium | Directed |  | PASSED | 20/9
2.1.3 | Count from 0, divide by 4 | 1. Wait for reset and clock stable 2. Write data 8'b01 to TIE register 3. Write data 8'b10001 to TCR register 4. Wait 1040 posedege ker_clk 5. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_div4_test |  | Directed |  | PASSED | 20/9 | The s_ovf signal is NOT LOW after being asserted
2.1.4 | Count from 0, divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b01 to TIE register 3. Write data 8'b11001 to TCR register 4. Wait 2100 posedege ker_clk 5. Read value of TDR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_div8_test |  | Directed |  | PASSED | 20/9 | The s_ovf signal is NOT LOW after being asserted
2.1.5 | Count from random, no divide | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b01 to TIE register 5. Write data 8'b01 to TCR register 6. Wait 300 - (random value) posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_rd_div1_test |  | Random |  | PASSED | 22/9
2.1.6 | Count from random, divide by 2 | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b01 to TIE register 5. Write data 8'b1001 to TCR register 6. Wait 600 - (random value) posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_rd_div2_test |  | Random |  | PASSED | 22/9
2.1.7 | Count from random, divide by 4 | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b01 to TIE register 5. Write data 8'b10001 to TCR register 6. Wait 1100 - (random value) posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_rd_div4_test |  | Random |  | PASSED | 22/9 | The s_ovf signal is NOT LOW after being asserted
2.1.8 | Count from random, divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b01 to TIE register 5. Write data 8'b11001 to TCR register 6. Wait 2100 - (random value) posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h01 | cnt_up_rd_div8_test |  | Random |  | PASSED | 22/9 | The s_ovf signal is NOT LOW after being asserted
2.1.9 | Count up from 0 with divide by 4, then change the counter at middle | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'b10001 to TCR register 4. Wait 520 posedege ker_clk 5. Write data 8'b10011 to TCR register 6. Wait 600 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_up_change_test |  | Directed |  | PASSED | 22/9 | The s_udf signal is NOT LOW after being asserted
2.2 | Count down
2.2.1 | Count from 0, no divide | 1. Wait for reset and clock stable 2. Write data 8'b10 to TIE register 3. Write data 8'b11 to TCR register 4. Wait 2 posedege ker_clk 5. Write data 8'b11 to TSR register 6. Wait 300 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_div1_test | High | Directed |  | PASSED | 24/9
2.2.2 | Count from 0, divide by 2 | 1. Wait for reset and clock stable 2. Write data 8'b10 to TIE register 3. Write data 8'b1011 to TCR register 4. Wait 2 posedege ker_clk 5. Write data 8'b11 to TSR register 6. Wait 600 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_div2_test | Medium | Directed |  | PASSED | 24/9
2.2.3 | Count from 0, divide by 4 | 1. Wait for reset and clock stable 2. Write data 8'b10 to TIE register 3. Write data 8'b10011 to TCR register 4. Wait 2 posedege ker_clk 5. Write data 8'b11 to TSR register 6. Wait 1100 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'h10 | cnt_dw_div4_test |  | Directed |  | PASSED | 24/9 | The s_udf signal is NOT LOW after being asserted
2.2.4 | Count from 0, divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b10 to TIE register 3. Write data 8'b11011 to TCR register 4. Wait 2 posedege ker_clk 5. Write data 8'b11 to TSR register 6. Wait 2100 posedege ker_clk 7. Read value of TDR register Pass condition: Check interrupt is asserted and read value is 8'h10 | cnt_dw_div8_test |  | Directed |  | PASSED | 24/9 | The s_udf signal is NOT LOW after being asserted
2.2.5 | Count from random, no divide | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b10 to TIE register 5. Write data 8'b11 to TCR register 6. Wait [(random value) + 30] posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_rd_div1_test |  | Random |  | PASSED | 26/9
2.2.6 | Count from random, divide by 2 | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b10 to TIE register 5. Write data 8'b1011 to TCR register 6. Wait [(random value)*2 + 30] posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_rd_div2_test |  | Random |  | PASSED | 26/9
2.2.7 | Count from random, divide by 4 | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b10 to TIE register 5. Write data 8'b10011 to TCR register 6. Wait [(random value)*4 + 30] posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_rd_div4_test |  | Random |  | PASSED | 26/9 | The s_udf signal is NOT LOW after being asserted
2.2.8 | Count from random, divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b10 to TIE register 5. Write data 8'b11011 to TCR register 6. Wait [(random value)*8 + 30] posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_rd_div8_test |  | Random |  | PASSED | 26/9 | The s_udf signal is NOT LOW after being asserted
2.2.9 | Count down from 0 with divide by 4, then change the counter at middle | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'b10011 to TCR register 4. Wait 520 posedege ker_clk 5. Write data 8'b11 to TSR register 6. Write data 8'b10001 to TCR register 7. Wait 600 posedege ker_clk 8. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_dw_change_test |  | Directed |  | FAILED | 26/9 | Clear data from TSR register, but underflow bit from TSR register is still value because the s_udf signal is NOT LOW after being asserted. The s_ovf signal is NOT LOW after being asserted
2.3 | Cross count up and count down
2.3.1 | Count up from 0, then changes to count down | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'b01 to TCR register 4. Wait 130 posedege ker_clk 5. Write data 8'b11 to TCR register 6. Wait 300 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_up_dw_test | Medium | Directed |  | PASSED | 28/9
2.3.2 | Count up from random, then changes to count down | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b11 to TIE register 5. Write data 8'b01 to TCR register 6. Wait 130 posedege ker_clk 7. Write data 8'b11 to TCR register 8. Wait 300 posedege ker_clk 9. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_up_dw_rd_test |  | Random |  | PASSED | 28/9
2.3.3 | Count down from 0, then changes to count up | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'b11 to TCR register 4. Wait 130 posedege ker_clk 5. Write data 8'b01 to TCR register 6. Wait 300 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_dw_up_test |  | Directed |  | PASSED | 28/9
2.3.4 | Count down from random, then changes to count up | 1. Wait for reset and clock stable 2. Write data 8'b100 to TCR register 3. Write random value of TDR register 4. Write data 8'b11 to TIE register 5. Write data 8'b11 to TCR register 6. Wait 130 posedege ker_clk 7. Write data 8'b01 to TCR register 8. Wait 300 posedege ker_clk 9. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b11 | cnt_dw_up_rd_test |  | Random |  | PASSED | 28/9
2.4 | Changes divide mode at middle
2.4.1 | Count up with no divide, then changes to divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h01 to TCR register 4. Wait 130 posedege ker_clk 5. Write data 8'h11001 to TCR register 6. Wait 1100 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_up_div_1_8_test | Medium | Directed |  | PASSED | 30/9
2.4.2 | Count up with divide by 2, then changes to divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h1001 to TCR register 4. Wait 300 posedege ker_clk 5. Write data 8'h11001 to TCR register 6. Wait 1100 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_up_div_2_8_test |  | Directed |  | PASSED | 30/9
2.4.3 | Count up with divide by 4, then changes to divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h10001 to TCR register 4. Wait 600 posedege ker_clk 5. Write data 8'h11001 to TCR register 6. Wait 1100 posedege ker_clk 7. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b01 | cnt_up_div_4_8_test |  | Directed |  | PASSED | 30/9
2.4.4 | Count down with divide by no divide, then changes to divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h11 to TCR register 4. Wait 10 posedege ker_clk 5. Read value of TSR register 6. Write data 8'b11 to TSR register 7. Wait 130 posedege ker_clk 8. Write data 8'h11011 to TCR register 9. Wait 1100 posedege ker_clk 10. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_div_1_8_test |  | Directed |  | PASSED | 30/9
2.4.5 | Count down with divide by 2, then changes to divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h1011 to TCR register 4. Wait 10 posedege ker_clk 5. Read value of TSR register 6. Write data 8'b11 to TSR register 7. Wait 300 posedege ker_clk 8. Write data 8'h11011 to TCR register 9. Wait 1100 posedege ker_clk 10. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_div_2_8_test |  | Directed |  | PASSED | 30/9
2.4.6 | Count down with divide by 4, then changes to divide by 8 | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'h10011 to TCR register 4. Wait 10 posedege ker_clk 5. Read value of TSR register 6. Write data 8'b11 to TSR register 7. Wait 600 posedege ker_clk 8. Write data 8'h11011 to TCR register 9. Wait 1100 posedege ker_clk 10. Read value of TSR register Pass condition: Check interrupt is asserted and read value is 8'b10 | cnt_dw_div_4_8_test |  | Directed |  | PASSED | 30/9
3 | Interrupt test
3.1 | Check underflow forward input | 1. Wait for reset and clock stable 2. Write data 8'b10 to TIE register 3. Write data 8'b11 to TCR register 4. Wait 255 posedge clk_in Pass condition: Check interrupt is asserted | underflow_en_test | High | Directed |  | PASSED | 2025-10-03
3.2 | Check underflow not forward input | 1. Wait for reset and clock stable 2. Write data 32'b11 to TCR register 3. Wait 255 posedge clk_in Pass condition: Check interrupt is not asserted | underflow_dis_test |  | Directed |  | PASSED | 2025-10-03
3.3 | Check overflow forward input | 1. Wait for reset and clock stable 2. Write data 8'b01 to TIE register 3. Write data 8'b01 to TCR register 4. Wait 255 posedge clk_in Pass condition: Check interrupt is asserted | overflow_en_test |  | Directed |  | PASSED | 2025-10-03
3.4 | Check overflow not forward input | 1. Wait for reset and clock stable 2. Write data 8'b01 to TCR register 3. Wait 255 posedge clk_in Pass condition: Check interrupt is not asserted | overflow_dis_test |  | Directed |  | PASSED | 2025-10-03
3.5 | Check underflow and overflow forward input | 1. Wait for reset and clock stable 2. Write data 8'b11 to TIE register 3. Write data 8'b01 to TCR register 4. Wait 255 posedge clk_in 5. Write 8'b11 to TSR register 6. Write data 8'b11 to TCR register 7. Wait 255 posedge clk_in Pass condition: Check interrupt is asserted | ud_over_en_test | Medium | Directed |  | PASSED | 2025-10-03
3.6 | Check underflow and overflow not forward input | 1. Wait for reset and clock stable 2. Write data 8'b01 to TCR register 3. Wait 255 posedge clk_in 4. Write 8'b11 to TSR register 4. Write data 8'b11 to TCR register 5. Wait 255 posedge clk_in Pass condition: Check interrupt is asserted | ud_over_dis_test |  | Directed |  | PASSED | 2025-10-03
4 | Check APB protocol |  |  |  | Assertion